## FMEA
| Doc# | FMEA#### |  |  |  |  | Revision | 01 |  |  | Scoring Scale | Severity(1-5)
| Doc Title | ReportRighter Risk Analysis |  |  |  |  | Date |  |  |  |  | Occurrence(1-5)
| Authors | [10 empty] | Detectability(1-5)
| Purpose | This docoument is used to assess the risk associated with integrating ReportRighter into your report writing process. This document is to be used as a starter to your internal risk assessment. |  |  |  |  | Critical RPN | 27
Line | Process Functions / Requirements | Potential Failure Modes | Potential Effects of Failure | Severity | Potential Causes of Failure | Occurrence | Current Controls/Detection | Detectability | RPN | Recommended Action | Action Taken | Severity | Occurrence | Detection | RPN
1 | Use ReportRighter command buttons | When clicking buttons the expected action does not occur | Unable to create/utilize automated document templates | 2 | ReportRighter not deployed to account, no internet access | 2 | ReportRighter is unable to function, no controls necessary | 1 | 4
2 |  | Task panes do not load | Unable to create/utilize automated document templates | 2 | No internet access | 2 | ReportRighter is unable to function, no controls necessary | 1 | 4
3 | Save Import Settings | Import settings are not saved with the document | Document template must be recreated, settings must be re-entered before importing data | 2 | Document not saved after settings were entered | 2 | ReportRighter is unable to create report, no controls necessary | 1 | 4
4 | Import Data | Incorrect Data Imported | The report does not accurately represent the results | 4 | Incorrect sheet/cell address entered in the settings, incorrect workbook was selected to import, workbook not properly compiled in Excel first, Import settings have been changed | 3 | ReportRighter's lock settings feature, other controls are at discretion of end user | 3 | 36 | Create a defined process for validating document templates, Review all reports to ensure data has been imported correctly
5 |  | Data imported to a location that should not have been replaced | Random data interrupting and eliminating information in the report | 4 | The section of text used as placeholders for import locations was not unique | 3 | Controls are at discretion of end user | 3 | 36 | Create a standard identification pattern for import locations
6 |  | Tables do not auto-size | Not all data was imported into the tables | 4 | Table settings not properly checked to match the repeat direction, data was not in contiguous cells in Excel | 2 | Controls are at discretion of end user | 3 | 24
7